## General
Expectations on Solution owner:
- Participate in the meetings initiated by the project resources and secure that we agree on what to migrate and what to “leave”. Also agree on a suitable wave for migrating each solution – the migration must be finalized before end of December 2014.
- Support & approve project technical staff access to PROD databases when needed, access to Test/Dev databases where this is possible to gain.
- When each wave is ended secure that all content in common My Folder area is moved My folders in 10.2 by each user. The project will not take care of My Folders migration only provide space to store the content. | The users will need to get reasonable time to move the My folders content
- Respect the freeze period that will start when the migration starts of each Solution and last until the BAT is done and solution accepted. Any changes done in PROD after migration day 1 will be lost! When BAT is done and migration accepted by the owner, the solution is available for further development.
- Test all migrated Solutions/reports to secure that all data is correct in the new version. In case of high volume of reports the project advices to test the most important so to secure that all connections to data sources is correct. After this Acceptance test the Solution Owner will accept the solution and the migration phase will close.
Note: in some areas e.g. CODA the project members have no access to PROD data in 8.4 and can therefore not test or secure that all data connections are correct – this has to be taken care of by each Solution Owner.
- All cosmetic changes to reports on the new platform will be handled by each Solution Owner.
- Update of current educational material for each local solution, will be handled by each Solution Owner
Findings/ Questions:

## Structure
Content descriptions to respective Business capability area
Created by IKEA Business architects
1.Strategy, Planning and Business development
–...
2.Range management
–Country range
–BIFF
–PCM CRM
–RM
3.Product requirements
–Customer experienced product quality
–Q study
4.Product development
–...
5.Product sourcing
–MISBASP
–MISPRID
–PDSUPFY
–Purchase agreement
–Supplier
–Supplier performance
6.Availability planning
–Available to customer
–Activity
–Demand
–Manual input to Need/Supply
–Fulfilment supply plan
–Supply plan accuracy
–Sales forecast visibility
7.Manufacturing
–...
8.Delivery operations
–Direct supply measurement
–Goods flow
–Lead-time
–Stock
–Transport cost
–Transport fill rate
–MOSE reporting
9.Merchandising
–Sales space usage
–Sales space opportunities
–Merchandising solution summary
10.Marketing
–MDB
11.Selling
–AD Sales – IDW
–Sales reporting
–STAT SALE 2FY YWS WI
–Statistical sales analysis
–Statistical sales strategic analysis
–Statistical sales tactical analysis
–SLM-Sales per m2
–SAMS
–Customer returns
–Weekly sales
–KPI dashboard
–Misc Internal RBI reports
–Retail Sales and Gross margin
–Store reporting
12.Business Performance and Insight
–GM/GP
13.Workforce and Talent Management
–...
14.Financial management
–EuroPricing
–MDQ
–Yearly runs average DWP
–Finalyser
–CODA reporting
–Cost management tool
–Finance DWH
–FRESCO
–IVAN
–RIMS
–Transfer pricing RU
–CAIS
15.Support
–CBD reporting
–‘IICG reporting’
16.Information technology
–Audit
–Monitoring
–System information
17.Sustainability
§SCP ODS solutions?
§Functional dashboards (roles)
§Process dashboards
IKEA Business Capability Model, IBCM, Level 1
Level 2 Business capabilities
Strategy, Planning and Business development
  Group strategy development, IKEA Business planning, Business development, Enterprise risk management, Enterprise architecture
Range management
  Range design, Range life cycle management, Spare part management
Product requirements
  Requirements identification, Requirement implementation, Service specification, Product deviation management
Product development
  Innovation management, Products and share solution management, Intellectual property management, Service offer development, Product information, Sales solution development
Product sourcing
  Purchase development, Supply chain network design, Supplier base development, Agreement/ Contract management, Foreign trade management
Availability planning
  Demand forecasting, Supply planning, Global inventory optimisation, Distribution network optimisation, Capacity planning
Manufacturing
  Production planning, Production, Production logistics operations
Delivery operations
  Order management, Delivery management, Warehouse management, Import/ Export operations
Merchandising
  Assortment planning, Sales steering, Pricing management, Sales space planning, Promotion management
Marketing
  Commercial communication, Customer insight, Campaign management, Media production, Loyalty program management
Selling
  Self service buying, Returns management, Assisted buying, Recovery, Customer service
Business Performance and Insight
  Business performance management, Business information management, Business intelligence, analytics and insight
Workforce and Talent Management
  Talent management, Co-worker information management, Payroll, Attracting rewarding and retaining, Staff planning, Time reporting
Financial management
  Payable management, Accounting, Customer payments, Tax management, Receivable management, Consumer financing and business credit, Cost and pricing intercompany, Financial and statutory reporting, financial asset management, Investment management
Support
  Corporate communication, Property management, Collaboration
Information technology
  Planning and Organising information technology, Acquiring and implementing solutions, Delivering and supporting solutions, Monitoring and evaluation

## DirectSupplyMeasurement
|  | Solution owner comment: | Upgrade project comment:
Name of solution: | Direct Supply Measurement | Migrate late, since there are changes ongoing
Wave: | 4 (weeks 47-50)
SLA | 07.07.2011
Handover documentation | n/a
C8.4 report path: | Public Folders > Availability > Goodsflow > Direct Supply Measurement
Root folder 10.2: | 08 Delivery Operations
C10.2 report path: | 08 Delivery Operations > Direct Supply Measurement
Business owner: | Annette Sodano
Solution Owner: | Peter Larsson |  | Network id: PEON
Service manager: | Jonas Bergman
Service owner: | Anna Skattum
Application manager: | Subhasis Raha
Support manager: | Reiner Jechimer
Incident manager: | Thomas Krüger
Problem manager: | Petra Petersson
Infrastructure manager: | Dinesh Adhikari
Database/ Application: | (CNS (Cargo Network Services) system, Athena, Helena, Freja, PIA) > IDW
Service name: | direct supply measurement
Packages: | - DSM Standard Package - DSM Adhoc Package | Peter checks if the reports in the packages can be removed | Report [Standard package]: Range% ? Report [Adhoc package): HFB% ?]
Reports: | Main reports: - (folder) Open - DSM - Supply Chain Total - DSM - Category - DSM - CPG - DSM - DS Area - DSM - Range Name - DSM - HFB - DSM - Product Name - DSM - Region - Country - DSM - Retail Unit - DSM - Trading Area Drill Troughs: - (folder) Open - [20 reports] | Reports in Open has more details (and also more filters) Possibly some reports can be left in C8.4 Update 20/11/14: all reports are to be migrated | What does the folders 'Open' indicate?
Package update frequency: | DSM data should be updated first Wednesday in each month. But it is important that the update contains a full month of data so some months the update can not run the first Wednesday due to that the Wednesday is the first or second day in that month. In those months the update will be on the 2: nd Wednesday in that month.
Can be Open for read-only for all (Y / N): |  | Yes | Are there any information that must have limited access?
Related C8.4 CDS groups: | - DirectSupplyMeasurement_Owner - DirectSupplyMeasurement_SuperUser - DirectSupplyMeasurement_QueryUser | Almost all in SC has gotten access to this solution, and then all got QS access Most information is also available in QV, but Retail users will still use Cognos
Capability groups: |  | Read only Query user | What types of Cognos tools should be used?
Content groups: |  |  | Can all users see same content?
Approval structure:
Additional access needed to run solution:
Description of business usage: | The Direct Supply Measurement is calculating how big the Direct Supply share is from the total goods flow. The goods are measured from the receiving perspective, meaning that only volumes received in the Store, CDC, and LSC are considered. The measurement is based on the goods flow in net cubic meter. |  | About 1000 users (?)
Targeted user roles:
IKEA inside homepage:
User documentation:
E-learning/s:
Overall concerns on solution: |  | Pretty straight forward reports (almost all use about the same layout)
Usage of Burst area (Y/N): |  | No
if Y, what is the business need?
Usage of External data (Y/N):
if Y, what is the business need?
Samples of proper 'prompt input' per report |  | Peter will provide that
Data need for migration (freshness, range etc.), database for Dev and Test
Number standard reports in BAT |  | 5 - 10 reports (including drill reports)
Usage audit (average run time, usage frequency, number of users etc.)
Public folders
Packages
Reports
Exchange area |  |  | Clean up
Dashboard |  |  | There are audit reports which are to be put in the Administration > Audit folder: Public Folders > Availability > Goodsflow > Direct Supply Measurement > Dashboards > Dashboards Components
Administration (Audit)
Solution owner area |  |  | Empty
My folders

## GoodsFlowAdvanced
|  | Solution owner comment: | Upgrade project comment:
Name of solution: | Goods flow advanced GFA Standard Measurement reports | n/a
Wave: | 4 (weeks 47-50) | Would like to have this moved to Wave 4
SLA | 14.12.2010
Handover documentation | n/a
C8.4 report path: | Public Folders > Availability > Goodsflow > Goodsflow Advanced
Root folder 10.2: | 08 Delivery Operations
C10.2 report path: | 08 Delivery Operations > Goods Flow Advanced
Business owner: | Giedre Krysen
Solution Owner: | Peter Larsson |  | Network id: PEON
Service manager: | Jonas Bergman
Service owner: | Anna Skattum
Application manager: | Subhasis Raha
Support manager: | Reiner Jechimer
Incident manager: | Thomas Krüger
Problem manager: | Petra Petersson
Infrastructure manager: | Dinesh Adhikari
Database/ Application: | (CNS, PIA, Helena, Athena, Athena, Freja) -> IDW
Service name:
Packages: | - Goodsflow - Goodsflow Advance
Reports: | (folder) DSA Team Queries - (folders [7]) (folder) GFA Standard Measurement Reports (folder) Retail Logistics (folder) STP Queries (folder) Supply Team - CDC Outflow GFA HFB - Goodsflow Measurement ESEN FY10 - Goodsflow Measurement total north | Peter will look into what is standard, and what should be migrated Update 20/11/14: all reports are to be migrated | Clean up?
Package update frequency: | Publishing of the Goodsflow Advanced new figures is done weekly and the new data is available Tuesdays at 12.00 CET.
Can be Open for read-only for all (Y / N): |  | No (there are some price information which cannot be disclosed to everyone) | Are there any information that must have limited access?
Related C8.4 CDS groups: | Cognos_GoodsflowAdvanced_Owner Cognos_GoodsflowAdvanced_SuperUser Cognos_GoodsflowAdvanced_QueryUser Cognos_GoodsflowAdvanced_ReportAuthor | Peter checks | Report studio: Giedre, Steve Hutton, Olof Krantz, Binglu Tang and Federica Barberis?
Capability groups: |  | Read Query studio Report studio (or lighter C10.2 tool ...?) | What types of Cognos tools should be used?
Content groups: |  |  | Can all users see same content?
Approval structure:
Additional access needed to run solution:
Description of business usage: | Follow up the conect goods flow figures in all regions. The common base for lIiliA co'workers to follow up the historical goodsflow from sender to receiver on several aggregation levels, in an easy way |  | About 1000 users (?)
Targeted user roles: | - DS Flow & Capacity planner - Supply Developer Receiver - Supply Planner - Transport Business Navigator - Retail logistics Capacity & Flow Planner - IoS Business Navigator
IKEA inside homepage:
User documentation:
E-learning/s:
Overall concerns on solution: |  | Some preparations musts be done by the Solution owner There are some business users who have been granted RS access
Usage of Burst area (Y/N): |  | No
if Y, what is the business need?
Usage of External data (Y/N):
if Y, what is the business need?
Samples of proper 'prompt input' per report |  | Peter will provide that (there are not really any Standard reports, but mainly lists)
Data need for migration (freshness, range etc.), database for Dev and Test
Number standard reports in BAT |  | ?
Usage audit (average run time, usage frequency, number of users etc.)
Public folders
Packages
Reports
Exchange area |  |  | 75 entries; clean up
Dashboard |  |  | There are audit reports which are to be put in the Administration > Audit folder: Public Folders > Availability > Goodsflow > Goodsflow Advanced > Dashboards > Dashboards Components
Administration (Audit)
Solution owner area
My folders
The Super-Users are responsible for: • Questions regarding bUSiness processes • Reporting structure • Education and Instructions • Answer questions for the users of the solution.